## Week4
| DAILY TASK TRACKER | Check your tasks for the week, add any missing tasks and complete the number of days you have worked and required time to complete the task
Malith
Day | Task Brief | Status | Start Time | End Time | Elapsed Time | Percentage Completed | Project Start date | Project Due on | Required time
In progress
0
0
0
0
0
0
Monday | power cut |  |  |  | 0
0
Tuesday | jeson website new content updates /New home page and old home page | Done | 10:00 | 13:00 | 0.125 | 100% | 2020-11-18 | 2020-11-28
| salesforce developer intermidiate | In progress | 13:30 | 18:00 | 0.1875 | 20%
Wednesday | jeson website black color banner changes updated | Done | 10:00 | 11:00 | 0.041667 | 100% | 2020-11-18 | 2020-11-28
0
0
Thursday | stepnie product images | Done | 10:00 | 14:00 | 0.16667 | 100% | 2020-12-24 | 2020-12-24
0
Friday | dayout |  |  |  | 0
0
0
Saturday | donna report document | Done | 10:00 | 12:00 | 0.083333 | 100% | 2020-12-14 | 2020-12-24
| webflow training - kasun ayya / create two pages | Done | 14:00 | 18:00 | 0.16667 | 100%
0
Monday |  |  |  |  | 0
Tuesday | milton website document changes updated | Done | 10:00 | 12:00 | 0.083333 | 100% | 2020-11-08 | 2020-11-06
| jude website tab form sample create/mulistate box | Done | 14:00 | 17:00 | 0.125 | 100%
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Formulas:
Elapsed Time = ([End Time]-[Start Time])

## Week3
| DAILY TASK TRACKER | Check your tasks for the week, add any missing tasks and complete the number of days you have worked and required time to complete the task
Malith
Day | Task Brief | Status | Start Time | End Time | Elapsed Time | Percentage Completed | Project Start date | Project Due on | Required time
In progress
0
Monday | Veronice most of changes completed(25 pages word file) | Done | 10:00 | 17:00 | 0.29167 | 100% | 2020-10-28 | 2020-11-06
| Start donna site home page | In progress | 17:00 | 18:00 | 0.041667 | 5% | 2020-12-14 | 2020-12-24 | 1 day
0
Tuesday | donna website site homa page | Done | 10:00 | 18:00 | 0.33333 | 100% | 2020-12-14 | 2020-12-24
0
Wednesday | donna site other pages design | Done | 10:00 | 18:00 | 0.33333 | 100% | 2020-12-14 | 2020-12-24
| Booking form design complete | Done | 10:00 | 18:00 | 0.33333 | 100% | 2020-12-14 | 2020-12-24
0
Thursday | donna coding client side | In progress | 10:00 | 18:00 | 0.33333 | 100% | 2020-12-14 | 2020-12-24 | 1 day
0
Friday | donna backend coding/client side coding | Done | 10:00 | 18:00 | 0.33333 | 100% | 2020-12-14 | 2020-12-24
0
Saturday | donna site create video website demostraion | Done | 10:30 | 15:00 | 0.1875 | 100% | 2020-12-14 | 2020-12-24
| dona site booking form input validation added | Done | 15:00 | 17:00 | 0.083333 | 100% | 2020-12-14 | 2020-12-24
| bookiing form check payment | Done | 17:00 | 18:00 | 0.041667 | 100% | 2020-12-14 | 2020-12-24
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Formulas:
Elapsed Time = ([End Time]-[Start Time])

## Week2
| DAILY TASK TRACKER | Check your tasks for the week, add any missing tasks and complete the number of days you have worked and required time to complete the task
Malith
Day | Task Brief | Status | Start Time | End Time | Elapsed Time | Percentage Completed | Project Start date | Project Due on | Required time
In progress
Monday | bottlefed website video create | Done | 10:00 | 12:00 | 0.083333 | 100% | 2020-11-23 | 2020-11-27
Tuesday | Mark Quay website Lending home page | Done | 10:00 | 17:00 | 0.29167 | 100% | 2020-12-08 | 2020-12-11
| Mark Quay Lending home page mobile view | Done | 17:00 | 18:00 | 0.041667 | 100% | 2020-12-08 | 2020-12-11
0
Wednesday | phoebe site , home page completed. services page completed. about page completed. contact page completed. All pages mobile view fixed. | Done | 10:00 | 18:00 | 0.33333 | 100% | 2020-12-02 | 2020-12-11
0
Thursday | mark quay-lending web site Home page completed All Services pages completed(include dummy contents) About Us page completed Contact Us page completed All Pages mobile view Fixed | Done | 10:00 | 18:00 | 0.33333 | 100% | 2020-12-08 | 2020-12-11
0
0
Friday | quay-lending web site changes | Done | 10:00 | 14:00 | 0.16667 | 100% | 2020-12-08 | 2020-12-11
| phoebe web site changes | Done | 14:00 | 17:00 | 0.125 | 100% | 2020-12-02 | 2020-12-11
0
Saturday | phoebe site changes dark mood | Done | 10:00 | 14:00 | 0.16667 | 100% | 2020-12-02 | 2020-12-11
| phoebe site change the wireframe design dark theme |  |  |  | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Formulas:
Elapsed Time = ([End Time]-[Start Time])

## Week1
| DAILY TASK TRACKER | Check your tasks for the week, add any missing tasks and complete the number of days you have worked and required time to complete the task
Malith
Day | Task Brief | Status | Start Time | End Time | Elapsed Time | Percentage Completed | Project Start date | Project Due on | Required time
In progress
Wednesday | jeson webite book-private-tours page created, mobile view done. bookings-form page created, mobile view done. contact us page created, mobile view done. | Done | 10:00 | 18:00 | 0.33333 | 100% | 2020-11-18 | 2020-11-28
| bottlefedbaby custom contact form | Done | 10:00 | 18:00 | 0.33333 | 100% | 2020-11-23 | 2020-11-27
0
Friday | joshua -pasindu - home page - Malith updates | Done |  |  | 0
| Bottlefedbaby - Wix Corvid - MALITH doc and video/changes | Done | 10:00 | 18:00 | 0.33333 | 100% | 2020-11-23 | 2020-11-27
| John - Wix - Malith website | Done | 10:00 | 18:00 | 0.33333 | 100% | 2020-12-04 | 2020-12-07
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Formulas:
Elapsed Time = ([End Time]-[Start Time])

## Names
Name
Add name of employee | Time | Day
Ruchiran
Sanju | 0.375
| 0.33333 | Monday
| 0.35417 | Tuesday
| 0.375 | Wednesday
Gayashan | 0.39583 | Thursday
Kasun Mendis | 0.41667 | Friday
Thishara | 0.4375 | Saturday
Pasindu | 0.45833 | Sunday
Malith | 0.47917
Shazni | 0.5
0.52083
0.54167
0.5625
0.58333
0.60417
0.625
0.64583
0.66667
0.6875
0.70833
0.72917
0.75
0.77083