## Week4
| DAILY TASK TRACKER | Check your tasks for the week, add any missing tasks and complete the number of days you have worked and required time to complete the task
Malith
Day | Task Brief | Status | Start Time | End Time | Elapsed Time | Percentage Completed | Project Start date | Project Due on | Required time
In progress
Monday | robert - MALITH- Create all pages | Done | 8:00 | 18:30 | 0.4375 | 100% | 2020-10-26 | 2020-10-26
Tuesday | robert website fixed changes | Done | 8:00 | 12:00 | 0.16667 | 100% | 2020-10-26 | 2020-10-26
| camella fixed changes | Done | 12:30 | 15:00 | 0.10417 | 100% | 2020-10-19 | 2020-10-29
| Mark Orford fixed some changes (not all) | In progress | 15:00 | 17:00 | 0.083333 | 50% | 2020-10-08 | 2020-10-17 | 1 day
Wednesday | Mark Orford updates completed | Done | 9:00 | 14:00 | 0.20833 | 100% | 2020-10-08 | 2020-10-17
| robert website changes completed | Done | 14:30 | 17:30 | 0.125 | 100% | 2020-10-26 | 2020-10-26
Thursday | carmella new updates done | Done | 9:00 | 15:00 | 0.25 | 100% | 2020-10-19 | 2020-10-29
| mark website mobile view Done | Done | 15:00 | 18:00 | 0.125 | 100% | 2020-10-08 | 2020-10-17
Friday | mark website userguide pdf | Done | 9:00 | 10:30 | 0.0625 | 100% | 2020-10-08 | 2020-10-17
| robert website table completed add all values | Done | 11:00 | 18:00 | 0.29167 | 100% | 2020-10-26 | 2020-10-26
Saturday | jordon site updates completed | Done | 9:00 | 15:00 | 0.25 | 100% | 2020-09-14 | 2020-10-19
| robet mobile view | Done | 15:30 | 17:30 | 0.083333 | 100% | 2020-10-26 | 2020-10-26
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Formulas:
Elapsed Time = ([End Time]-[Start Time])

## Week3
| DAILY TASK TRACKER | Check your tasks for the week, add any missing tasks and complete the number of days you have worked and required time to complete the task
Malith
Day | Task Brief | Status | Start Time | End Time | Elapsed Time | Percentage Completed | Project Start date | Project Due on | Required time
In progress
Monday | zach - COSMELAN page,Plamere Plasma Pen Treatment page,Vascular Laser Treatment page done.. mobile view done.. | In progress | 9:00 | 18:30 | 0.39583 | 70% | 2020-10-20 | 2020-10-19
Tuesday | Zack -check pages and fixed changes | Done | 9:00 | 11:00 | 0.083333 | 100% | 2020-10-20 | 2020-10-19
| Carmella - try to understand requirments | In progress | 11:00 | 12:00 | 0.041667 |  | 2020-10-19 | 2020-10-29
| Carmella-create staff member,create booking services and check when booking product then chek the email,when booking chech two different pages | In progress | 12:00 | 17:00 | 0.20833 |  | 2020-10-19 | 2020-10-29
Wednesday | Carmella -grammer check,check grid lines,create doc | In progress | 9:00 | 17:00 | 0.33333 |  | 2020-10-19 | 2020-10-29
Thursday | Carmella create doc and fixed updates | In progress | 9:00 | 17:00 | 0.33333 |  | 2020-10-19 | 2020-10-29
Friday | Carmell fixed home page design | Done | 9:00 | 14:30 | 0.22917 | 100% | 2020-10-19 | 2020-10-29
| robert-create homepage | In progress | 15:00 | 17:00 | 0.083333 | 50% | 2020-10-26 | 2020-10-26 | 1 day
0
Saturday | robert home page | Done | 9:00 | 14:30 | 0.22917 |  | 2020-10-26 | 2020-10-26
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Formulas:
Elapsed Time = ([End Time]-[Start Time])

## Week2
| DAILY TASK TRACKER | Check your tasks for the week, add any missing tasks and complete the number of days you have worked and required time to complete the task
Malith
Day | Task Brief | Status | Start Time | End Time | Elapsed Time | Percentage Completed | Project Start date | Project Due on | Required time
In progress
Monday | Mark Orford - wix Malith -fix home page,create sub pages,connect database sub pages ,fix header and footer | In progress | 9:00 | 18:00 | 0.375 | 50% | 2020-10-08 | 2020-10-12 | 1
Tuesday | Mark Orford - wix Malith -fix all pages | In progress | 9:00 | 17:30 | 0.35417 |  | 2020-10-08 | 2020-10-10
Wednesday | Mark Orford - wix Malith -fix support pages,brands pages | In progress | 9:00 | 17:30 | 0.35417 |  | 2020-10-08 | 2020-10-10
Thursday | Mark Orford - wix Malith-add store fridges pages | In progress | 9:00 | 17:30 | 0.35417 |  | 2020-10-08 | 2020-10-10
Friday | Mark Orford - wix Malith-add store all pages | In progress | 8:00 | 15:00 | 0.29167 |  | 2020-10-08 | 2020-10-10
| Jordon - wix - malith -fixing updates | In progress | 15:00 | 17:30 | 0.10417 |  |  | 2020-10-12
Saturday | Jordon - wix - malith -add price list add add 2 price sections | Done | 10:00 | 11:00 | 0.041667
| Old page and New page changes | Done | 15:00 | 17:00 | 0.083333
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Formulas:
Elapsed Time = ([End Time]-[Start Time])

## week1
WEEKLY TASK TRACKER | Check your tasks for the week, add any missing tasks and complete the number of days you have worked and required time to complete the task
Malith
Task | Status | Days Worked | Percentage Completed | Start date | Due on | Required time
In progress
jataka | Done
mark | In progress |  |  | 10.08.2020 | 10.11.2020
ogpcgaming | In progress |  |  | 10.05.2020 | 10.11.2020
serkan | In progress |  |  | 10.06.2020 | 10.11.2020

## Names
Name
Add name of employee | Time | Day
Ruchiran
Sanju | 0.375
| 0.33333 | Monday
| 0.35417 | Tuesday
| 0.375 | Wednesday
Gayashan | 0.39583 | Thursday
Kasun Mendis | 0.41667 | Friday
Thishara | 0.4375 | Saturday
Pasindu | 0.45833 | Sunday
Malith | 0.47917
Shazni | 0.5
0.52083
0.54167
0.5625
0.58333
0.60417
0.625
0.64583
0.66667
0.6875
0.70833
0.72917
0.75
0.77083